## Slide 1
Component 3: Climate resilience and low carbon strategies developed
Activity Progress and Component Strategy

## Slide 2: Activity Progress May-Oct 2012
Climate change risk assessment in BCI sites in Lao PDR, Thailand and Viet Nam completed and reports finalized
  Site reports for all three countries and synthesis report completed
  Assessment methodology used as a platform for (e.g. USAID ADAPT, Mekong ARCC GMS Core Agriculture Support Program, WB-WWF Ecosystem Based Adaptation)
REDD+ activity concepts developed and partners mobilized
  LoAs for Lao PDR, Thailand and Viet Nam prepared in consultation with government and non-government partners
  Official approval received for the activity from all three countries
Low carbon / green freight pilot project concepts developed as a result of Carbon Neutral Transport Corridor feasibility study
  Feasibility study final reports drafted and investment proposal for Low Carbon Transport Corridors prepared
  Green Freight Initiative pilot projects concept paper developed in consultation with private sector and government partners

## Slide 3
Component 3
Climate resilience and low carbon strategies developed
ADAPTATION AND CLIMATE RESILIENCE
1. Climate change modelling/ monitoring capacity building
2. Risk assessment and identification of adaptation interventions
3. Testing and replication of adaptation options
NATIONAL SFM AND REDD+ READINESS
1. Strengthening national REDD+ planning and policy
2. Strengthening forest and carbon monitoring systems
3. Testing and development of REDD+ systems
MITIGATION
1. NAMA awareness raising and policy / planning support
2. Technical capacity building for mitigation MRV systems
3. Testing and development of low carbon interventions
Objectives:
Contribute to knowledge base on climate change and build monitoring capacity / MRV systems
Identify the feasibility of climate change interventions
Test interventions in selected sites with an emphasis on developing institutional / financing mechanisms

## Slide 4: Results-based planning
2013
Up-to-date climate change modelling methods and outputs developed
At least 30 stakeholders trained
National REDD+ roadmap established & participatory monitoring systems tested
30 communities engaged in carbon stock assessment
Increased awareness on NAMAs & Green Freight pilot projects implemented
At least 30 officials trained & 10% fuel use reduction in 300 trucks
2014
Capacity identify cost effective adaptation interventions improved
Adaptation interventions identified in at least 3 BCI sites
Scope of community level institutions in BCI sites expanded to implement REDD+ projects
Prior consent and agreements on REDD+ with 30 communities
MRV capacity improved
GHG MRV system tested for one sector
2015
Scope of community level institutions in BCI sites expanded to include adaptation
Ecosystem based adaptation interventions tested in at least 30 communities
MRV/ REL system methodologies harmonized across the region
Uniform monitoring across BCI sites in 3 countries
Feasibility of low carbon community interventions assessed
Potential interventions identified
2016
At least three investment proposals on low-carbon technologies and / or climate change adaptation prepared
At least 1 national, provincial, or city-based MRV systems developed
Pilot projects with private sector on low carbon technologies implemented in at least one sector
Adaptation
REDD+
Mitigation

## Slide 5: Priorities for the next six months
Climate Change Adaptation (Regional)
  Mobilize partnerships with SEA START, CSIRO, national universities/ research institutions, I-NGO partners
  Organize round table meeting in January to identify knowledge gaps
REDD+ Readiness (THA, LAO, VIE)
  LAO, VIE: Develop participatory carbon monitoring methodology (REDD+) and hold training of trainers for testing these (in partnership with SNV and WWF)
  THA: Provide implementation support to R-PLAN, conduct social assessment to design benefit distribution systems
Green Freight pilot projects (THA, LAO, VIE)
  Initiate formal discussions with government agencies
  Organize study tour to China Green Freight pilot projects in Guangzhou
  Engage implementing partners and initiate approval process